## Sheet1
Activity | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
HVAC UNIT DELIVERED
INSTALL HVAC | 1
INSTALL DUCTS | 2
INSTALL DIFFUSERS | 1
HVAC START/TEST | 2
HVAC BALANCING | 1
FRAMING | 1
DRYWALL | 1
DRYWALL FINISHES | 4
INSTALL CEILING GRID | 1
INSTALL CEILING TILES | 1
ROUGH-IN, ABOVE CEILING, INSPECTION | 3
CONNECT HVAC | 1
INSTALL LIGHTING FIXTURES | 2
ELECTRICAL TRIM OUT | 2
PAINT DRYWALL | 2
INSTALL RUBBER BASE | 1
INSTALL CARPET | 1

## Sheet1 (6)
Activity | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
HVAC UNIT DELIVERED
INSTALL HVAC | 1
INSTALL DUCTS | 2
INSTALL DIFFUSERS | 1
HVAC START/TEST | 2
HVAC BALANCING | 1
FRAMING | 1
DRYWALL | 1
DRYWALL FINISHES | 4
INSTALL CEILING GRID | 1
INSTALL CEILING TILES | 1
ROUGH-IN, ABOVE CEILING, INSPECTION | 3
CONNECT HVAC | 1
INSTALL LIGHTING FIXTURES | 2
ELECTRICAL TRIM OUT | 2
PAINT DRYWALL | 2
INSTALL RUBBER BASE | 1
INSTALL CARPET | 1

## Sheet1 (5)
Activity | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
HVAC UNIT DELIVERED
INSTALL HVAC | 1
INSTALL DUCTS | 2
INSTALL DIFFUSERS | 1
HVAC START/TEST | 2
HVAC BALANCING | 1
FRAMING | 1
DRYWALL | 1
DRYWALL FINISHES | 4
INSTALL CEILING GRID | 1
INSTALL CEILING TILES | 1
ROUGH-IN, ABOVE CEILING, INSPECTION | 3
CONNECT HVAC | 1
INSTALL LIGHTING FIXTURES | 2
ELECTRICAL TRIM OUT | 2
PAINT DRYWALL | 2
INSTALL RUBBER BASE | 1
INSTALL CARPET | 1

## Sheet1 (4)
No. | Activity | Predecessor | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
1 | HVAC CREW
2 | HVAC UNIT DELIVERED
3 | INSTALL HVAC | 2 | 1
4 | INSTALL DUCTS | 9 | 2
5 | INSTALL DIFFUSERS | 12 | 1
6 | HVAC START/TEST | 14 | 2
7 | HVAC BALANCING | 6,13 | 1
8 | DRYWALL CREW
9 | FRAMING |  | 1
10 | DRYWALL | 9,15 | 1
11 | DRYWALL FINISHES | 10 | 4
12 | INSTALL CEILING GRID | 11 | 1
13 | INSTALL CEILING TILES | 5,17 | 1
14 | ELECTRICAL CREW
15 | ROUGH-IN, ABOVE CEILING, INSPECTION | 9 | 3
16 | CONNECT HVAC | 3 | 1
17 | INSTALL LIGHTING FIXTURES | 12 | 2
18 | ELECTRICAL TRIM OUT | 13,20 | 1
19 | FINISHING CREW
20 | PAINT DRYWALL | 11 | 2
21 | INSTALL RUBBER BASE | 22 | 1
22 | INSTALL CARPET | 1,8,14,20 | 1

## Sheet1 (2)
Activity | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40

## Sheet1 (3)
Activity | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40